## Implementation Plan
Automation Implementation Plan
Tools: Excel VBA / Python Scripts · Free, no licence required · 9 Worktypes · 28 Solutions
# | Worktype | Solution | Tool | Dev (Days) | Test (Days) | UAT (Days) | Total (Days)
1 | Pre-Renewals — Ad Hoc | Log incoming ad hoc requests | Excel VBA / Python | 2 | 1 | 1 | 4
2 | Captive Payment | Log and track payment requisitions | Excel VBA / Python | 3 | 1 | 1 | 5
3 |  | Generate draft approval email content | Excel VBA / Python | 2 | 1 | 1 | 4
4 | Captive Receipt | Log incoming receipts | Excel VBA / Python | 2 | 1 | 1 | 4
5 |  | Generate draft notification email content | Excel VBA / Python | 1 | 1 | 0.5 | 2.5
6 | OAR Payment | Apply business rules to OAR Excel sheet | Excel VBA / Python | 4 | 2 | 2 | 8
7 |  | Apply post-confirmation business rules (FX calc) | Excel VBA / Python | 3 | 2 | 2 | 7
8 |  | Fill OAR Matrix | Excel VBA / Python | 2 | 1 | 1 | 4
9 |  | Track OAR payment status | Excel VBA / Python | 2 | 1 | 1 | 4
10 | OAR Receipt | Apply business rules to OAR Excel sheet | Excel VBA / Python | 1 | 1 | 1 | 3
11 |  | Fill OAR Matrix | Excel VBA / Python | 1 | 0.5 | 0.5 | 2
12 |  | Track OAR receipt status | Excel VBA / Python | 1 | 0.5 | 0.5 | 2
14 | Dividend Payments (USD / Direct Wire) | Validate Confirmation Number format before PRISM entry | Excel VBA / Python | 1 | 1 | 0.5 | 2.5
17 | Captive Template Preparation | Read Matrix and determine template type | Excel VBA / Python | 2 | 1 | 1 | 4
18 |  | Copy files from previous quarter | Python Script | 1 | 1 | 1 | 3
19 |  | Rename files per quarter naming convention | Python Script | 1 | 1 | 0.5 | 2.5
20 |  | Unprotect all workbooks | Excel VBA / Python | 1 | 1 | 0.5 | 2.5
21 |  | Apply business rules across all templates | Excel VBA / Python | 4 | 2 | 2 | 8
22 |  | Update Matrix with completion status | Excel VBA / Python | 1 | 0.5 | 0.5 | 2
23 | GGA Template Preparation | Read Matrix and determine template type | Excel VBA / Python — Reuse | — | 0.5 | 0.5 | 1
24 |  | Copy files from previous quarter | Python Script — Reuse | — | 0.5 | 0.5 | 1
25 |  | Rename files per quarter naming convention | Python Script — Reuse | — | 0.5 | 0.5 | 1
26 |  | Unprotect all workbooks | Excel VBA / Python — Reuse | — | 0.5 | 0.5 | 1
27 |  | Apply business rules across all templates | Excel VBA / Python | 3 | 2 | 2 | 7
28 |  | Update Matrix with completion status | Excel VBA / Python — Reuse | — | 0.5 | 0.5 | 1
TOTAL |  |  |  | 38 | 25 | 23 | 86

## Summary
Summary — Time Estimates by Worktype
Worktype | Solutions | Dev (Days) | Test (Days) | Total (Days)
Pre-Renewals — Ad Hoc | 1 | 2 | 1 | 4
Captive Payment | 2 | 5 | 2 | 9
Captive Receipt | 2 | 3 | 2 | 6.5
OAR Payment | 4 | 11 | 6 | 23
OAR Receipt | 3 | 3 | 2 | 7
Dividend Payments (USD / Direct Wire) | 2 | 4 | 2 | 2.5
Captive Template Preparation | 6 | 10 | 6.5 | 22
GGA Template Preparation | 6 | 3 | 4.5 | 12
TOTAL | 26 | 41 | 26 | 86
Notes
1 development day = 8 working hours
Test days = internal testing by the development team
UAT days = testing with the business team
Reuse = solution reused from another worktype — 0 development days, testing only